# Claims Copilot Meridian Charter

Claims Copilot / Meridian 2026 Accelerated Scope

Contents

Executive Summary	3

Program/Project	3

Problem Statement	3

Project Objectives and Value	3

Opportunity Cost	3

Scope	4

Assumptions	4

Risks	4

Communication Plan	5

Dependencies	5

Resources Needed	5

Summary of References	5

Architecture	5

Quality Attributes	6

Test Strategy	6

Warranty	6

Run and Maintain / Project Closeout	6

Benefit Realization Metrics & Tracking	6

Notes/Comments	6

Appendix	7

Architecture Intake	7

Technical Architecture	7

Quality Attributes and Priority	7

Test Strategy and Approach	8

Test Strategy and Responsibilities	10

Revision History	10

# Executive Summary

Accelerate Claims Copilot integration into Meridian in 2026 to establish Meridian as the client-facing front door for claims, with Claims Copilot serving as the underlying claims transaction and data analytics engine. The program funds one-time build, integration, country readiness, and initial operational support required to enable priority country/client rollout in 2026 and broader scale beginning in 2027. The program comprises three workstreams – Client Experience Build and Appian-side configuration / colleague E2E experience enhancement, Integration & APIs, and Test/Deployment/Launch Readiness. Claims Analytics is included in the overall client experience but is being delivered by the ACIA team and is out of scope for the Provider under this RFP.

Missing: final approved project file name, formal approval status, and confirmed executive sponsor details.

| Project/Program Name | Claims Copilot Meridian Integration | Projected Start Date | 1 September 2026 (Project Kick-Off Target, per RFP) |
| --- | --- | --- | --- |
| Sponsors | Bill Hooper Adam Ellis | Projected End Date | 31 March 2027 |
| Risk Capital IT Owner | Adam Ellis | Product Director | Saulius Valentinavicius |
| Overall Sponsor/Exec | Mona Barnes | Project Manager | Paul Sargent |

# Program/Project

#### Problem Statement

Risk Capital needs a scalable client-facing claims experience that can support international rollout through Meridian while continuing to use Claims Copilot for claims transaction processing, claims data, workflow, analytics, and integration services.

For clients and Aon colleagues who need a consistent global entry point for claims status, claim initiation, documents, activity, and analytics

who require secure, localized, persona-relevant access to claims information across countries, clients, and hierarchies

the Claims Copilot Client Experience

is a Meridian-enabled client interface and integration capability that provides claims landing pages, eFNOL, claim status, document access, analytics, APIs, and access control alignment.

Unlike standalone or country-specific claims entry points that require separate access, inconsistent workflows, and fragmented integration patterns

our product enables a consistent Meridian front door with SSO, RBAC/entitlements, Claims Copilot workflow integration, country readiness, and scalable global rollout foundations.

Missing: confirmation of final country/client launch list, cross-border data restrictions, and whether Claims Copilot launches as an independent application with SSO/UI integration only where MDM readiness is incomplete Claims Client Experience eis delivered as a Micro-Frontend injected into the Meridian shell; a dedicated, independent Claims Copilot portal was assessed and rejected, and a Meridian-owned Claims UX was assessed as a viable secondary option only. Final country/client launch list and the global data residency / cross-border transfer model remain open items in the RFP (see Architecture Decisions and Open Items for Providers).

#### Project Objectives and Value

The project will deliver the foundation for a scaled global Claims Copilot rollout through Meridian by enabling a client-facing claims landing page, localized eFNOL, claims status and activity views, document access, analytics, APIs, and integration with Meridian identity and entitlement patterns. The 2026 accelerated scope is expected to support an initial rollout planning assumption of approximately 100 clients in 10 countries, with broader rollout following in 2027 as country, privacy, access, and ODS readiness come online. Business value includes improved client experience, stronger consistency across Risk Capital digital channels, reduced fragmentation across country portals, and reusable integration patterns for future global expansion. The functional baseline for this scope comprises 8 epics and 44 features, with a consolidated set of 51 non-functional requirements (NFR-01 to NFR-51) treated as acceptance criteria.

#### Opportunity Cost

If the 2026 acceleration is not funded, Claims Copilot may remain less integrated with Meridian, limiting near-term client-facing rollout, reducing continuity on in-flight work, and delaying country readiness needed for international scale. The alternative is to continue with a narrower or independent Claims Copilot launch path, which may defer a consistent Meridian user experience, reusable entitlement model, ODS country enablement, and MDM-aligned hierarchy integration. Per RFP, the current-state channels being replaced are the AonLine and DASP microsites, with claim registration frequently occurring out-of-band by email or telephone and status enquiries routed through an Aon Claims Administrator rather than self-service.

#### Scope

Scope includes the 2026 accelerated build and integration work required to make Meridian the client-facing front door for Claims, with Claims Copilot as the claims transaction and data analytics engine. The project includes Claims Copilot client experience capabilities, Meridian integration, ODS country enablement, access control alignment, API/data integration, and program/change management support. Per the finalized RFP, delivery is structured across three workstreams – Workstream 1 (Client Experience Build), Workstream 2 (Integration and APIs), and Workstream 3 (Test, Deployment and Launch Readiness) – underpinned by three integration design pillars: DMS Alignment (Pillar 1), RBAC Integration (Pillar 2) and User Portal Integration (Pillar 3).

The scope includes a UI/UX component for the Claims Client Experience landing page, user navigation, localized eFNOL flows, and Meridian-aligned client experience design.

In Scope:

In scope: Meridian landing page integration; multi-language capability; dynamic eFNOL request form for web and mobile; workflow integration to Claims Copilot; claim status indicators; document storage/retrieval; DocuSign for eFNOL where approved; configurable alternate hierarchies; RBAC/client access management; MDM client hierarchy integration; Claims Copilot APIs and data shares; ODS country enablement; and change/program management. Per RFP, in-scope also explicitly includes: native iOS and Android mobile applications (in addition to a responsive web/browser experience – not solely responsive web); WCAG 2.2 Level AA accessibility conformance; the S-DMS proxy-over-ECM document access pattern (Pillar 1); ACORD-based carrier messaging via CCS; and presentation of Claims Analytics (the analytics build itself is delivered by the ACIA team and is out of scope for the Provider).

- MVP :

  - High-impact claims overview landing page deep-linked from Meridian; claims status/activity summary; dynamic localized eFNOL initiation; persona- and client-relevant claims data; initial API and workflow integration; and access via shared identity. Claims Administrator Workbench, Aon colleage E2E experience enhancement (Appian) and all internal Claims Copilot business logic;

- MMP

  - Production-ready integrated Claims Copilot/Meridian capability for priority clients and countries, including RBAC/entitlements, document access, claim initiation, claim status, activity stream, core analytics entry points, country-ready integrations, and operational support model.

- Remaining Project Scope

  - Remaining Project Scope: scaled rollout readiness for additional countries/clients in 2027; expanded API catalogue; additional country portal integrations; additional document management integrations; and continued refinement of country-specific privacy, access, and data restrictions.

- Out of Scope:

  - Specific countries and clients not approved for 2026 rollout; capabilities requiring unresolved country privacy/access approvals; ACIM unless explicitly approved; and unrelated Human Capital Meridian scope such as Global Benefits, Wealth, Flex Benefits, Captive Management, Multinational Pooling Tool, and renewal tracker build. The Claims Analytics build and the Claims Copilot → Claims Analytics Platform data feed is not in the direct scope and delivered by the ACIA team.

- Parking Lot:

  - Potential parking lot items include additional countries beyond the 2026 priority rollout, deeper country portal integrations, expanded DocuSign coverage, additional global product integrations, ACIM domiciles if later approved, and broader document management enhancements. Per RFP, this also includes full S-DMS migration with ECM decommission (dual-repository synchronisation assessed and deferred) and Meridian Integration Level 5 (full Meridian stack integration).

High Level Sprint Plan

High-level delivery forecast: mobilize funding and teams in 2026; complete integrated build across Claims Copilot, Meridian integration, ODS enablement, and change/program management; prepare priority countries and clients for initial rollout as country readiness, privacy, access, and dependency decisions are resolved; scale rollout beginning in 2027 as capabilities come online. Per the finalized RFP, the seven payment milestones and tentative dates are: M1 Contract & Mobilization (10%, 11 Sep 2026); M2 Requirements & Architecture Sign-off (15%, 30 Sep 2026); M3 Design & MVP Completion (20%, 6 Nov 2026); M4 Development & SIT Completion (25%, 4 Dec 2026); M5 UAT Sign-off (15%, 30 Dec 2026); M6 Production Go-Live (10%, 15 Feb 2027); M7 Hypercare Exit (5%, 31 Mar 2027).

This is NOT a commitment. Timelines are forecasts based on current backlog, team capacity, country readiness, dependency resolution, and available funding. Priorities within the high-level plan are expected to shift and should be refined after approval.

Sample: 
Missing: sample sprint/Gantt visualization for this specific engagement – to be produced once the Provider's project plan is submitted (RFP Round 1 due 28 Aug 2026; Round 2/Final due 3 Sep 2026).

Sprint 0 – Discovery/Planning

Sprint 1

Value/Feature Delivered

Sprint 2

Value/Feature Delivered

le

Sprint 3

Value/Feature Delivered

le

Sprint 4

Value/Feature Delivered

le

Sprint 5

Value/Feature Delivered

Sprint 6

Value/Feature Delivered

  - le

Sprint 7

Value/Feature Delivered

le

Sprint 8

Value/Feature Delivered

le

Sprint 9

Value/Feature Delivered

le

Sprint 10

Value/Feature Delivered

le

Sprint 11

Value/Feature Delivered

le

Sprint 12

Value/Feature Delivered

  - le

Sprint 13

Value/Feature Delivered

le

Sprint 14 – Post Launch

#### Assumptions

The following assumptions underpin the scope, budget, and timeline estimates.

| Assumption | Comments/Mitigation Plan |
| --- | --- |
| 2026 funding approval is obtained for the accelerated scope and teams can mobilize in time to preserve continuity on in-flight work. | Mitigation: confirm funding decision, prioritization, and governance before committing to delivery dates. Engage preferred vendor(s) quickly, simplified RPF process. |
| Initial rollout planning assumes approximately 100 clients in 10 countries, subject to final country/client prioritization. | Missing: final country and client list, launch sequencing, and rollout acceptance criteria. |
| The Provider engagement model is fixed-outcome, fixed-fee, deliverables-based across seven milestones, per the finalized RFP; Aon does not accept blended rates. | Confirmed by RFP; alternative payment weightings will not be accepted. |
| Provider staffing follows Aon's planning assumption of ~89% offshore delivery, per the RFP Team Composition and Roles baseline (8 epics / 44 features already scoped in Azure DevOps). | Mitigation: require at least one alternative resourcing plan and evidenced onshore/offshore rationale, as required by the RFP. |

#### Risks

Known risks before project start include country readiness, data/privacy/compliance constraints, dependency delivery, access control complexity, and integration unknowns.

| Risk | Comments/Mitigation Plan |
| --- | --- |
| Country complexity, data privacy, cross-border access restrictions, and integration unknowns could delay rollout or increase cost. | Mitigation: retain contingency, complete country readiness assessment, confirm privacy/access requirements, and sequence rollout based on readiness. |
| MDM client hierarchy integration and Meridian entitlement capabilities may not be ready or complete for all launch scenarios. | Mitigation: confirm minimum access model, assess whether interim SSO/UI integration is acceptable, and define fallback controls. Consider partial / later MDM implementation. |
| The MDM → Okta organisational scope binding mechanism and refresh frequency (R-14) and the Okta configuration for Client User groups/custom claims (OI-26) are open items per RFP that determine entitlement latency and RBAC build effort. | Mitigation: resolve in the MDM/RBAC deep-dive workshops scheduled from mobilization; do not baseline the RBAC design deliverable until both are confirmed. |
| Performance/load testing and Aon-executed penetration testing share a compressed window (7–18 December 2026 per RFP), which could affect remediation and retest turnaround ahead of UAT sign-off (30 Dec 2026). | Mitigation: confirm dedicated resourcing for concurrent performance and penetration test support. |
| The accelerated timeline, solution complexity, and cross-team dependencies may delay milestones, UAT, or go-live. | Mitigation: confirm the critical path, assign dependency owners, track risks weekly, and re-phase scope if needed. |

#### Communication Plan

Communication plan should follow the AMR’D framework with regular delivery governance across Claims Copilot, Meridian Integration, ODS, Claims Integration, Claims Client Experience, Program/Change Management, business stakeholders, and executive sponsors. Executive reporting should focus on funding approval, scope decisions, country readiness, dependency health, risk mitigation, and rollout readiness. Aon operates a tiered governance model spanning executive steering, solution-line oversight and programme delivery via the Meridian TMO.

Missing: agreed governance cadence, meeting owners, steering committee membership, escalation path, and reporting template.

#### Dependencies

Dependencies include Meridian entitlement management and RBAC/client access configuration, Okta SSO, MDM client hierarchy mapping into Claims Copilot, ODS country enablement, Claims Analytics/Insights integration, document repository and document retrieve APIs, country portal readiness, MCP-enabled APIs, Databricks Unity Catalog publication, and UI/UX design support. The target-state architecture names nine participating business/technology services: Claims Copilot (BS-01), Meridian (BS-02), CCS/Carrier Connectivity (BS-03), MDM (BS-04), the Claims Analytics Platform (BS-05, delivered by the ACIA team), ODS/Policy Data (BS-06), Okta/Aon IdP (TS-01), S-DMS (TS-02) and ECM/FileNet (TS-03).

Missing: named owners, dependency delivery dates, environment readiness, and confirmed decision on whether Claims Copilot can launch independently with SSO/UI integration only.

#### Resources Needed

Resources are estimated across Product/Project Management, Development, Business, and SME groups. Budget estimates include 2026 requested funding of $3.23M and 2027–2029 ongoing funding of $2.96M. Per RFP Team Composition and Roles, the Provider-side delivery team is expected to include (indicatively, India/Poland/US-based): 1 Architect, 1 Enterprise Agentic Architect, 1 Lead Developer, 3 Full Stack Developers, 3 QA Engineers with Automation, 1 Scrum Master, 1 DevOps Engineer, 1 RBAC Full Stack Developer, 1 UX/UI Full Stack Developer, 1 API Developer, 2 Data Engineers, 2 Appian Developers, 1 Technical Integration Lead and 1 Project Manager, plus an optional AMS team (3 L2 Support, 2 Data Ops) post-hypercare – approximately 89% offshore per Aon's planning assumption.

| Product/Project Management (PdM, PO, SM, PM, PgrM, RAPg Representative, etc) |  |  |
| --- | --- | --- |
| Role | Name | New Resource (Yes/No) |
| Product Manager / Product Owner / Program Manager / Change Manager / Project Manager | Missing: named resources | Yes / TBD |

| Development Team (Architect, BA, Dev Lead, Dev, QA Lead, QA, QA Automation, Data Services, UI/UX, etc.) |  |  |
| --- | --- | --- |
| Role | Name | New Resource (Yes/No) |
| Architect; Full Stack Developer; QA Engineer with Automation; AMS/Data Ops QA; API Developer; Data Engineer; Appian Developer; Technical Integration Lead; Business/Data Analyst; UX/UI Designer; Global Administrator (Per RFP Team Composition and Roles – headcounts and locations detailed above; Capacity Plan due with Provider proposal.) | Missing: named resources | Yes / TBD |

| Business Team (Executive Sponsor, Primary Stakeholder, Stakeholders, Design Group, SMEs, etc) |  |  |
| --- | --- | --- |
| Role | Name | New Resource (Yes/No) |
| Executive Sponsor; Primary Business Stakeholders; Claims Client Experience stakeholders; country readiness stakeholders; client access/entitlement owners; privacy/compliance stakeholders (Per RFP Aon Resources: Product Owner, Business Analyst, Business Data Analyst, Principal Enterprise Architect, Claims Integration Data Architect, Solution Architect/Design Authority, Meridian TMO, Legal/Privacy/Compliance, Working Group and Country/Pilot Leads.) | Missing: named stakeholders | TBD |

| SMEs (DevSecOps, Frameworks, etc.) |  |  |
| --- | --- | --- |
| Role | Name | New Resource (Yes/No) |
| DevSecOps; Architecture/RAPg; Security; Privacy; Compliance; MDM/Reltio; Okta/Identity; ODS; Databricks/Data Platform; Document Management; Country Portal SMEs (Per RFP: also includes MDM/Reltio, Okta/Identity, ODS, Databricks, Document Management (ECM/S-DMS), CCS/Carrier Connectivity and Country Portal SMEs for the pilot countries.) | Missing: named SMEs and contacts | TBD |

# Summary of References

#### Architecture

Logical architecture includes Aon Meridian as the client-facing front door with Claims Copilot UI/Appian supporting claim initiation, adjudication, management, settlement and payment. Target-state integrations include Okta SSO, RBAC/client access configuration, Claims Lakehouse, Claims Copilot DB, reference data APIs, business APIs, document management/repository services, country portals, CRS Ecosystem ODS, PMS integrations, MDM/Reltio, task management, global time tracking, claims payment, Claims Analytics, and AI agents. Per RFP, the solution must be built to the Meridian Pattern reference architecture: Layer 1 (UUI design system, mandatory for all client-facing UI), Layer 2 (Okta identity/SSO, mandatory – no custom identity stores permitted), Layer 3 (Google Agents/Vertex AI for future agentic capability), Layer 6 (Databricks Lakehouse, mandatory for all analytical data assets), and Layer 7 (Claude Code, the mandatory AI coding assistant for the engagement). The target Meridian Integration Level is Level 4 (Micro-Frontend embedding, SSO, application-managed RBAC, Meridian UI pattern compliance, centralized RBAC and Meridian data stack integration), with a defined path to Level 5 (full Meridian stack integration) as agentic and analytics capability matures.

#### Quality Attributes

Initial quality attribute priorities should emphasize security/access control, quality, scalability/performance, modifiability, time to market, and scope completeness. These priorities should be reviewed by architecture and business stakeholders because the solution handles client claims information, documents, cross-border access considerations, and multiple integration dependencies. All 51 consolidated NFRs (NFR-01 to NFR-51) are treated as acceptance criteria, including WCAG 2.2 Level AA accessibility (NFR-48 to NFR-50), phase-1 concurrency of 1,000 users and complexity-tiered response targets (NFR-24 to NFR-31), and a minimum 70% automated regression coverage.

#### Test Strategy

Test strategy should cover UI, API, workflow, data validation, access/entitlement, SSO, document management, country integration, eFNOL, regression, automation, performance, and UAT. Testing will require coordination across Claims Copilot, Meridian, ODS, document management, identity/access, and country portal teams. Functional testing is executed in-sprint with two-way requirement traceability, a minimum 70% automated regression suite runs on every CI/CD build, and system integration/end-to-end testing spans user journeys UJ-001 (FNOL Initiation) and UJ-002 (Claims Access and Monitoring) across all nine participating services.

#### Warranty

A 6-week hypercare/warranty period runs from Production Go-Live (tentative 15 Feb 2027) to Hypercare Exit (Milestone M7, 5% of fee, tentative 31 Mar 2027), during which all defects identified are resolved or formally accepted by Aon, evidenced by stable incident/defect trends before formal closure. Beyond hypercare, Aon has the option (at its discretion) to engage the Provider for continued Application Managed Services (AMS) covering L2 support and data operations, priced separately in the proposal.

#### Run and Maintain / Project Closeout

Run, maintain and continuous enhancement will require ongoing Claims Copilot product/support capacity (dedicated pod), Meridian AMS support, Claims Client Ops/global administration, data operations, integration support, and operational procedures for country enablement, access management, and client configuration. 2027–2029 ongoing funding is estimated at $1.89M CapEx and $1.08M Opex across Claims Copilot and Meridian Integration. The optional post-hypercare AMS scope covers L2 support and data operations, priced separately by the Provider and exercised at Aon's discretion.

Missing: maintenance handoff document, support model RACI, incident process, service levels, and BAU ownership. 1/2/3 support model, runbooks, escalation paths and on-call model are a Milestone M6 deliverable; the detailed RACI and BAU ownership model remain to be defined with the selected Provider.

#### Benefit Realization Metrics & Tracking

Benefit realization should track whether the 2026 investment enables the targeted integrated build, readiness for initial rollout, and the foundation for 2027 scale. Candidate measures include number of priority countries made ready, number of clients enabled, percentage of required integrations completed, eFNOL adoption, claims status/document access usage, entitlement configuration completion, rollout defects, and stakeholder readiness. Per RFP, candidate measures also include: percentage of the 51 NFRs and WCAG 2.2 AA accessibility conformance achieved; automated regression coverage (target ≥70%); on-time delivery against the seven payment milestones; and SIT/UAT defect counts by severity.

Strategic Initiative or Theme: Meridian client-facing digital experience and Claims Copilot global scale.

Business Value: consistent claims front door, improved client experience, faster international rollout readiness, reusable integration/access patterns, and reduced fragmentation.

Success: approved 2026 funding, delivered integrated build, priority country readiness, initial client rollout readiness, and clear 2027 scale path.

Leading Measures: dependency burndown, access model readiness, API readiness, ODS enablement progress, country readiness status, test completion, and UAT progress.

Lagging Measures

Lagging Measures: clients enabled, countries launched, eFNOL usage, claims status/document access adoption, production defects, support volumes, and realized operational/client experience benefits.

# Notes/Comments

# Appendix

Appendix should include the logical architecture, detailed financial estimate, sprint roadmap once confirmed, resource plan, country/client rollout plan, maintenance handoff, and dependency tracker. Per RFP, this also includes the Provider's Capacity Plan (Excel pricing template), the Non-Functional Requirements compliance matrix (NFR-01 to NFR-51), and the PowerPoint Provider Deck – all due with the first-round (28 Aug 2026) and second/final round (3 Sep 2026) submissions.

#### Architecture Intake

| Intake Question | Response (Y/N) |
| --- | --- |
| 1. Are any new 3rd party software or tools being used or being considered to build this solution? If you are unsure, reach out to RAPg. | Yes – Meridian Pattern components new to this application include the Databricks Lakehouse (Layer 6), Google Agents/Vertex AI for future agentic capability (Layer 3), Claude Code as the mandatory AI coding assistant (Layer 7), the UUI design system, and the S-DMS (DocuSign-based) proxy over ECM. |
| 2. Are there any new or to-be-deprecated technologies being investigated or research as a part of the project? Refer to the RAPg's Reference Architecture documentation for a list of current technologies. | Yes – the boundary between the Appian low-code core, Google Cloud services referenced at Meridian Pattern Layers 3/4, and the Azure-hosted Aon technology stack is to be reconciled during the design phase. |
| 3. Is this extending an existing pattern or architecture? | Yes – extends the existing Claims Copilot (Appian) colleague platform with new client-facing scope, built to the Meridian Pattern reference architecture, targeting Integration Level 4 with a path to Level 5. |
| 4. Will an external party be communicated or interacted with as a result? | Yes – external Client Users (client organisations) interact directly via Meridian, and the solution integrates with insurance carriers via CCS/ACORD messaging. |
| 5. Are there any open decisions/questions around architecture or how to deliver a technical aspect of the project? | Yes – open items include the MDM → Okta scope-binding mechanism (R-14), Okta configuration for Client User groups/custom claims (OI-26), and ECM/S-DMS metadata harmonization (DR-1.4/DR-1.5). |
| 6. Do any stakeholders have concerns about performance or scalability regarding either current or future project pieces? | Yes – phase-1 concurrency of 1,000 users, complexity-tiered response targets (NFR-24 to NFR-31), and 100MB file handling are Must-priority NFRs requiring dedicated performance/load testing (7–18 Dec 2026 window). |
| 7. Will you require the Training Environment for this project? (If yes, you must inform Tom Schneider/DevSecOps). | Missing: confirmation of training environment need – training/enablement is a Milestone M6 deliverable per RFP; to be scoped with the awarded Provider and DevSecOps informed if required. |

#### Technical Architecture

< 1. A Conceptual Architecture Diagram – MUST be completed prior to Qualify or in very early Qualify. This is a critical portion of the pre-sale.

2. A more detailed Solution Architecture Diagram – Should be completed during qualify. This is a more detailed version of the architecture based on the initial Conceptual Architecture Diagram.> Missing: Conceptual and Solution Architecture diagrams specific to this charter – see RFP Figure 6 (the Meridian Pattern stack) and Figure 7 (target-state Claims Copilot/Meridian architecture) as source material to adapt.

#### Quality Attributes and Priority

| Rank | Attribute |
| --- | --- |
| 1 | Performance: Performance speaks to how fast applications and services respond as well as their ability to scale to take on seasonal or unexpected load. Users of highly performing applications should experience very little wait time and time-consuming activities are accomplished asynchronously. Highly performing applications typically come at the cost of modifiability, certain UI/UX features, and potentially time to market. Only IT facing / internal management software should have performance de-prioritized. How: How: Complexity-tiered response targets (NFR-24 to NFR-31: Simple 2–4s, Medium 5–7s, Complex 8–10s, Very Complex 10–15s, Extremely Complex 30–40s); phase-1 concurrency of 1,000 users; validated via Aon-approved load/stress tooling (Microfocus Performance Center / LoadRunner Enterprise), 7–18 Dec 2026. |
| 2 | Quality: Software products of high quality are generally free of defects, are highly available with built in redundancy, fault detection, recovery, prevention and offer a pleasant UI/UX experience. Careful consideration is required any time quality is not ranked 1 - 3​ How: How: All 51 NFRs treated as acceptance criteria with a Comply / Comply with Qualification / Not Comply compliance matrix; WCAG 2.2 AA conformance audited per release; ≥70% automated regression coverage; MySQL InnoDB Cluster HA with Group Replication; 99% availability across business hours. |
| 3 | Modifiability: Modifiability is concerned with minimizing the cost of change. Highly modifiable systems allow changes of one component, without it taking too much effort or cost to change. This quality should be prioritized when it’s expected that the product will go through lots of changes over its lifespan and less prioritized if the frequency of change is small. Prioritizing modifiability typically comes at the expense of performance and time to market. How: How: Solution must be configurable rather than bespoke (Rules Engine/Workflow Configuration, Dynamic FNOL Forms, RBAC-based policy visibility) so new countries, clients, product lines and hierarchies onboard via configuration, not custom development – required for the 2027 global scale-up. |
| 4 | Time to Market: Time to market speaks to how important it is to hit a particular date with a specific set of features within a specific budget. Prioritizing time to market typically comes at the expense of scope, modifiability and potentially performance in order to beat a competitor to market. How: How: Compressed ~6-month build (1 Sep 2026 – 15 Feb 2027 phased launch) against seven fixed milestones; providers must state explicitly whether milestone dates are accepted and flag any milestone considered unachievable immediately. |
| 5 | Scope Completeness: This quality attribute speaks to the need to have a certain depth and breadth of features in order to have a viable product. A higher ranking indicates it is necessary to have most if not all o f the features delivered in order to recognize the benefits. Prioritizing scope completeness comes at the cost to 'Time to Market'. How: How: Full delivery of the three workstreams, the 8-epic/44-feature backlog, and the FNOL field inventory and claims list/claim record field model is necessary to realize the target client experience end to end. |
| 6 | Security: Chose a ranking of 6 if current security levels afforded by GRiDS frameworks are acceptable. Core services that play an intrinsic role in GRiDS security should prioritize this attribute as well as services that are susceptible to hacking attempts. Highly secure systems not only have robust authentication and authorization capabilities but also have proactive threat / intrusion monitoring and response. How: How: Confidential data classification and Significant application risk rating; Okta SSO/MFA at every entry point; organisational scope enforcement (BR-001 to BR-008); document provenance control (S-DMS/ECM); penetration testing executed by Aon with Provider remediation of all critical/high findings. |

#### Test Strategy and Approach

| Scope of Testing | Responses |
| --- | --- |
| 1. Are there integrations between GRiDS and other systems or applications? If yes, list out the systems/applications. | No GRiDS. Yes – Meridian shell, Okta (Aon IdP), MDM, ODS/CCP, S-DMS, ECM/FileNet, the Claims Analytics Platform (delivered by ACIA), and CCS (ACORD P&C/Surety XML Chapter 12). |
| 2. Will there be other Development teams testing than GRiDS Development teams? If yes, list involved teams. | Yes – the selected Provider's own QA Engineers with Automation (Claims Client Experience and Core Claims Copilot teams), plus the Aon security team executing penetration testing. |
| 2 a) Who is the other team(s) (vendor, Aon team)? | Provider QA (Claims Client Experience: 2x QA Engineer with Automation; Core Claims Copilot: 1x QA Engineer with Automation) and the Aon security team (penetration testing, executed by Aon). |
| 2 b) Who is the point of contact for other testing team(s)? | Missing: named points of contact – to be confirmed at Milestone M1 Team Mobilisation. |
| 2 c) What deliverables and/or handoff is expected from other testing teams? Note: Other development team(s) need to follow the GRiDS QA processes including artifacts in ADO. | Functional test suite with two-way traceability handed over as a maintainable, documented asset; automated regression pack (≥70% coverage) executing on every CI/CD build; accessibility conformance record per release; NFR compliance matrix. |
| 2 d) Are there exceptions to GRiDS QA team being responsible for Test Case Creation, Maintenance, and Execution? If yes, update the Test Strategy – Responsibilities section below. | No – other development team(s) (the Provider) are expected to follow Aon's SDLC and produce artefacts in Azure DevOps consistent with Aon's existing engineering governance. |
| 3. Please list any Critical Functionality to be priority for testing | Critical functionality: FNOL submission and the resilient submission path under simulated Claims Copilot outage; organisational scope enforcement (BR-001 to BR-008) and negative testing; document provenance control (client-provided policy documents never surfaced to Aon Brokers). |
| 4. What types of testing are included in the project? (e.g., UI, API, Data Validation) Any special or specific testing skill sets needed? | UI, API, workflow, data validation, access/entitlement, SSO, document management, country/localization, eFNOL, regression, automation, performance and load, resilience, accessibility (WCAG 2.2 AA) and security testing. |
| 5. Are there any non-standard tools being utilized for testing? | Specflow/Selenium/Microfocus-UFT (web/UI); BrowserStack/Selenium (browser); pCloudy (mobile); Postman/SoapUI (API); Microfocus Performance Center / LoadRunner Enterprise (performance/stress); YSlow/PageSpeed (client-side performance). |
| 6. Are there any known testing constraints (environmental, access, etc.)? E.g., No pre-production environment, No production access | Yes – performance/load testing and Aon-executed penetration testing share the same compressed window; UAT is Aon-led with Provider support, within a 5-day functional/regression execution window. |

| User Acceptance | Responses |
| --- | --- |
| 1. Who is responsible for coordinating, executing, and/or providing guidance for user acceptance testing? | Aon-led (Aon designees coordinate/execute UAT); the Provider provides UAT support and defect triage/resolution. |
| 2. Who is included in user acceptance testing? | Aon-designated business users and pilot client representatives across all in-scope capabilities and pilot countries. |

| Performance |  |  | Responses |  |
| --- | --- | --- | --- | --- |
| 1. If existing applications are impacted, what are the applications and the date of the last performance test? | App name | Baseline (avg) | Load (max user) N/A – new build | Stress (to failure) N/A – new build |
|  | ODS |  |  |  |
|  | FileNet |  |  |  |
|  | Claims Lakehouse (Databricks) |  |  |  |
|  |  |  | Performance/load/stress/soak testing executed 7–18 Dec 2026 (NFR-24 to NFR-31), witnessed by Aon; development-phase frequency to be confirmed at M2 Test & NFR Strategy sign-off. |  |
| 2. During Development, what is the expected frequency for baseline test? (e.g., end of each sprint, end of every 2 sprints, every pipeline deployment to QA environment, etc.) |  |  |  |  |
| 3. During Development, what is the expected frequency for load test? |  |  |  |  |
| 4. During Development, what is the expected frequency for stress test? |  |  | Missing: post-go-live baseline test cadence – to be defined during M6/M7 support model definition. |  |
| 5. Post Go-Live, what is the expected frequency for baseline test? |  |  | Missing: post-go-live load test cadence – to be defined during M6/M7 support model definition. |  |
| 6. Post Go-Live, what is the expected frequency for load test? |  |  | Missing: post-go-live stress test cadence – to be defined during M6/M7 support model definition. |  |
| 7. Post Go-Live, what is the expected frequency for stress test? |  |  |  |  |

| Test Automation | Responses |
| --- | --- |
| 1. If existing applications are impacted, do they have existing automation that will be impacted? | Yes – Claims Copilot colleague E2E experience is impacted, automation cases have to be built and adopted. |
| 2. Are there existing regression tests with automation? | N/A at RFP stage – the Provider is required to build a new automated regression pack achieving a minimum of 70% coverage, executing on every CI/CD build. |
| If yes, Is maintenance of existing regression test with automation in scope? |  |
| 3. Is automation of new regression tests in scope? | Yes – automation of new regression tests is explicitly in scope for the Provider, handed over to Aon as a maintainable, documented asset. |
| If no, will automation of new regression test go on the QA backlog for the Automation Core team? |  |

#### Test Strategy and Responsibilities

| Test Case Creation & Maintenance | Responses Per RFP: for the vendor-delivered Claims Client Experience scope, Provider QA (Claims Client Experience and Core Claims Copilot QA Engineers with Automation) owns test case creation and maintenance. Alignment with Aon's standard GRiDS QA model to be confirmed. |
| --- | --- |
| Who is responsible for test case creation & maintenance? If any variation, continue with the following questions. If no variation, then skip the following questions. | TBD |
| 1. Who is responsible to ensure that the test scenarios are defined? |  |
| 2. Who is on point to ensure Test Case work items are created in ADO? |  |
| 3. Who is responsible to ensure automation for the Test Cases/Scenarios are created? |  |
| 4. Who is responsible to ensure test case / scenarios are maintained? |  |
| 5. Who is responsible to ensure automation is maintained? |  |

| Test Case Execution | Responses Per RFP: Provider QA (Claims Client Experience and Core Claims Copilot QA Engineers with Automation) owns test case execution for the vendor-delivered scope; defect triage acceptance authority sits with the Aon Product Owner / Solution Architect. Alignment with Aon's standard GRiDS QA model to be confirmed. |
| --- | --- |
| Who is responsible for test case creation & maintenance? If any variation, continue with the following questions. If no variation, then skip the following questions. | TBD |
| 1. Who is responsible to ensure Bug work item is created in ADO for defects due to manual test case failure? |  |
| 2. Who is responsible for ensure the initial investigation of automation test case failure is completed? |  |
| 3. Who is responsible to ensure Bug work item is created in ADO for defects due to automation test case failure? |  |
| 4. Who is responsible for defect triage? |  |

#### Revision History

| Version # Date | Author | Modification(s) |
| --- | --- | --- |
| 0.1 17 Aug 2026 | Saulius Valentinavicius |  |