Meridian Claims Copilot

Client Experience

Proof of Concept — Build Plan

Step-by-step, screen-by-screen delivery approach with project structure

| Source RFP | Meridian_Claims_Copilot_Client_Experience_RFP_Ver1.0.docx |
| --- | --- |
| Companion document | Claims_Copilot_Meridian_Charter.docx |
| Issued by | Aon Global Spend Management (GSM) on behalf of Aon Service Corporation |
| Business unit | Commercial Risk Solutions ¦ Aon Business Services |
| Prepared | 21 August 2026 |
| Questions deadline | 21 August 2026 |
| Round 1 submission | 28 August 2026 |
| Round 2 / final | 3 September 2026 |
| Project kick-off target | 15 September 2026 |
| Target client launch | 15 February 2027 (phased) |

SCOPE This plan is derived entirely from the requirements, architecture decisions, business rules and non-functional requirements stated in the RFP. Every screen, field and acceptance test below carries a traceability reference back to its source clause.

Contents

| § | Section | Summary |
| --- | --- | --- |
| 1 | Purpose and Delivery Timing | Two-tier approach against the RFP calendar |
| 2 | What the POC Must Prove | The five proof points and their RFP anchors |
| 3 | Real versus Mocked Components | Honest boundary declaration for Aon |
| 4 | Project Structure | Full monorepo layout |
| 5 | Data Model | Schema grounded in Exhibit 5 |
| 6 | The Core Enforcement Function | BR-001 / F-CC-07 organisational scope |
| 7 | Sprint 0 — Foundation | Days 1 to 4: Okta, UUI stub, scope, MFE injection |
| 8 | Screen 1 — Claims Landing Page | Days 5 to 7 |
| 9 | Screen 2 — Claims List | Days 8 to 10 |
| 10 | Screen 3 — Claim Detail | Days 11 to 13 |
| 11 | Screen 4 — FNOL Wizard | Days 14 to 20 |
| 12 | Screen 5 — Notifications and Deep Link | Days 21 to 22 |
| 13 | Screen 6 — Analytics Placeholder | Day 23 |
| 14 | Screen 7 — Admin Configuration Console | Days 24 to 25 |
| 15 | Tier 1 Thin Slice | Seven days to a demoable build |
| 16 | Demo Script | Twelve-minute walkthrough |
| 17 | Compliance Evidence | Meridian Pattern alignment and NFR matrix |
| 18 | Open Questions for Aon | Items to raise before the deadline |

1.  Purpose and Delivery Timing

This document sets out how to build a proof of concept for the Meridian Claims Copilot Client Experience that is demonstrably aligned to the Meridian Pattern reference architecture, and that can be shown running rather than described on slides.

1.1  The calendar constraint

The RFP question deadline is 21 August 2026, Round 1 closes 28 August 2026 and Round 2 / final closes 3 September 2026. A full proof of concept cannot be completed before submission. The plan is therefore split into two tiers so that something credible is available for the clarification session while the fuller build continues behind it.

| Tier | Duration | Purpose |
| --- | --- | --- |
| Tier 1 — Thin Slice | Days 1 to 7 | Demoable in the Round 2 clarification session. Proves the three integration pillars work end to end. |
| Tier 2 — Full POC | Weeks 2 to 6 | Post-submission or post-award accelerator. All seven screens, full functionality, compliance evidence pack. |

RECOMMENDATION Build Tier 1 first and make sure it genuinely runs. In a clarification session a working seven-day demo carries more weight than a polished architecture deck, because it removes the evaluator's doubt about whether the pattern is understood.

1.2  Why this sequencing works

Sprint 0 establishes the three pillars. Everything after it is product surface built on a proven foundation.

Each screen is independently demoable, so slipping the last screen does not invalidate the demo.

The negative security tests are written on Day 3, before any UI exists, so scope enforcement cannot regress silently.

The configuration console is built last but rehearsed first, because it is the single most persuasive artefact in the pack.

2.  What the POC Must Prove

The strategic theme of the RFP, repeated in five separate places, is that the solution must be configurable rather than bespoke so that additional countries and clients can be onboarded without further engineering. Everything else is secondary to that. The POC should be architected to evidence that claim alongside the three integration pillars.

| Proof point | RFP anchor | How it is demonstrated |
| --- | --- | --- |
| Pillar 3 — MFE injection | ADR-003, DR-3.1 to DR-3.8 | Shell loads the Micro-Frontend at runtime over the network. Throw inside the MFE and the shell survives. |
| Pillar 2 — Organisational scope | BR-001, F-CC-07 | Same URL and same code, three personas, three different datasets. Enforced server-side. |
| Pillar 1 — Document provenance | BR-007, BR-008, NFR-05 | Internal and carrier-only documents never reach a client user. Filtered in the S-DMS proxy, not the UI. |
| Configurable not bespoke | NFR-45, Exhibit 5 | Edit a JSON configuration file, refresh the browser, the field appears. No rebuild, no redeploy. |
| Outage resilience | NFR-37, API Functionality (resilience) | Stop the Claims Copilot container, submit an FNOL successfully, restart and watch reconciliation issue the claim number. |

2.1  The requirement most bidders will under-answer

The RFP states plainly under Standard Functionality: in the event that Claims Copilot is unavailable, the client shall still be able to successfully submit a claim or incident via the claim notification tool, and there must be no client impact from an internal Claims Copilot outage. This is reinforced by NFR-37 as a Must.

Most responses will address this with a paragraph about queueing. Demonstrating it live — stopping the backend mid-demo and still completing a submission — converts a claim into evidence. It is the single highest-leverage thing in the POC and is described in full in section 11.

3.  Real versus Mocked Components

Aon must never be left with the impression that their enterprise systems have been replicated. Publish the table below in the POC README and state it verbally at the start of any demo. Declaring the boundary precisely is itself a credibility signal, and it makes the swap path auditable.

| System | POC approach | Swap path to production |
| --- | --- | --- |
| Okta | Real. Free developer tenant, real PKCE flow, real custom claims. | None required |
| United UI (UUI) | Stub package with an identical export surface and prop shapes. | Remove the stub dependency, add the Aon UUI package |
| Meridian shell | Shell Simulator — a real Module Federation host, not a mock. | Point the remotes entry at Aon's shell |
| Claims Copilot / Appian | Python FastAPI service using the real data model from Exhibit 5. | Replace the API client base URL |
| S-DMS / ECM FileNet | Mock proxy that enforces audience classification server-side. | Swap the transport inside sdms_proxy.py |
| MDM / Reltio | Seeded three-level hierarchy with materialised paths in MySQL. | Swap the resolver in mdm.py |
| ODS / CCP | Mock policy lookup keyed on site and date of loss. | Swap ods_ccp.py |
| CCS (ACORD) | Mock ACORD P&C XML emitter. | Swap ccs.py |
| Databricks | Out of POC scope. The transactional / analytical boundary is documented. | Not applicable — ACIA owns the analytics build |
| Claude Code | Real. Mandatory under Meridian Pattern Layer 7. | None required |

NOTE Okta and Claude Code are the two components used for real. That is deliberate: Okta is the mandatory identity layer under NFR-33 where custom identity stores are explicitly not permitted, and Claude Code is the mandated AI coding assistant under Layer 7. Using both for real means the two non-negotiable adoption rules are satisfied in the POC itself rather than promised.

4.  Project Structure

A pnpm monorepo keeps the shell, the Micro-Frontend and the shared design system in one place while preserving independent build and deployment of the MFE, which DR-3.7 requires.

claims-copilot-poc/ ¦-- README.md # real-vs-mock table, run instructions ¦-- docker-compose.yml # mysql + claims-api + mock-externals ¦-- pnpm-workspace.yaml ¦-- turbo.json ¦-- .env.example ¦ ¦-- docs/ ¦ ¦-- adr/ ¦ ¦ ¦-- ADR-POC-001-module-federation.md ¦ ¦ ¦-- ADR-POC-002-org-scope-single-enforcement-point.md ¦ ¦ ¦-- ADR-POC-003-config-driven-field-registry.md ¦ ¦ +-- ADR-POC-004-resilient-fnol-outbox.md ¦ ¦-- nfr-compliance-matrix.md # all 51 NFRs: Comply / Qualified / N/A ¦ ¦-- meridian-pattern-alignment.md # Layer 1-7 adoption rules ¦ +-- demo-script.md ¦ ¦-- packages/ ¦ ¦-- uui-stub/ # Meridian Pattern Layer 1 surrogate ¦ ¦ +-- src/ ¦ ¦ ¦-- tokens/ # color, spacing, type, radius ¦ ¦ ¦-- primitives/ # Button, TextField, Select, DatePicker, ¦ ¦ ¦ # Checkbox, Radio, Textarea ¦ ¦ ¦-- layout/ # PageHeader, Card, Grid, Tabs, Breadcrumb ¦ ¦ ¦-- data/ # DataTable, KpiTile, StatusPill, Timeline ¦ ¦ ¦-- feedback/ # Modal, Toast, Banner, Spinner, ErrorState ¦ ¦ ¦-- forms/ # FormField, FileUpload, Stepper ¦ ¦ +-- index.ts ¦ ¦ ¦ ¦-- contracts/ # shared types generated from OpenAPI ¦ ¦ +-- src/{claim,fnol,document,auth,field-registry}.ts ¦ ¦ ¦ ¦-- i18n/ # NFR-42 / NFR-43 / NFR-44 ¦ ¦ +-- locales/{en-US,es-ES,fr-FR,de-DE,ar-AE}.json ¦ ¦ ¦ ¦-- shell/ # ---- Meridian Shell Simulator ---- ¦ ¦ ¦-- src/ ¦ ¦ ¦ ¦-- auth/ ¦ ¦ ¦ ¦ ¦-- OktaProvider.tsx ¦ ¦ ¦ ¦ +-- deepLinkState.ts # DR-3.5 PKCE state encode / decode ¦ ¦ ¦ ¦-- layout/ ¦ ¦ ¦ ¦ ¦-- GlobalNav.tsx ¦ ¦ ¦ ¦ +-- EntitySwitcher.tsx ¦ ¦ ¦ ¦-- mfe/ ¦ ¦ ¦ ¦ ¦-- MfeHost.tsx # dynamic remote loader ¦ ¦ ¦ ¦ ¦-- MfeErrorBoundary.tsx # DR-3.4 ¦ ¦ ¦ ¦ +-- shellEventBus.ts # DR-3.8 ¦ ¦ ¦ +-- App.tsx ¦ ¦ +-- webpack.config.js # ModuleFederation: remotes ¦ ¦ ¦ +-- claims-mfe/ # ---- THE DELIVERABLE ---- ¦ ¦-- src/ ¦ ¦ ¦-- ClaimsApp.tsx # exposed root; receives props at mount ¦ ¦ ¦-- screens/ ¦ ¦ ¦ ¦-- landing/ ¦ ¦ ¦ ¦-- claims-list/ ¦ ¦ ¦ ¦-- claim-detail/ ¦ ¦ ¦ ¦-- fnol/ ¦ ¦ ¦ ¦ ¦-- steps/ # five wizard steps ¦ ¦ ¦ ¦ +-- engine/ # DynamicFormEngine ¦ ¦ ¦ ¦-- analytics/ # ACIA boundary placeholder ¦ ¦ ¦ ¦-- notifications/ ¦ ¦ ¦ +-- admin/ # config console (NFR-45 proof) ¦ ¦ ¦-- field-registry/ # Exhibit 5 attribute model client ¦ ¦ ¦-- entitlements/ # privilege guards from JWT groups ¦ ¦ ¦-- offline/ # IndexedDB drafts + outbox queue ¦ ¦ +-- api/ # typed client ¦ +-- webpack.config.js # ModuleFederation: exposes ¦ ¦-- services/ ¦ ¦-- claims-api/ # Python - Meridian Pattern service layer ¦ ¦ ¦-- app/ ¦ ¦ ¦ ¦-- main.py ¦ ¦ ¦ ¦-- auth/ ¦ ¦ ¦ ¦ ¦-- jwks.py # Okta JWKS validation ¦ ¦ ¦ ¦ +-- scope.py # F-CC-07 - THE enforcement point ¦ ¦ ¦ ¦-- routers/ ¦ ¦ ¦ ¦ ¦-- claims.py fnol.py documents.py ¦ ¦ ¦ ¦ ¦-- policies.py hierarchy.py contacts.py ¦ ¦ ¦ ¦ +-- notifications.py config.py ¦ ¦ ¦ ¦-- services/ ¦ ¦ ¦ ¦ ¦-- sdms_proxy.py # ADR-001 ¦ ¦ ¦ ¦ ¦-- outbox.py # NFR-37 resilience ¦ ¦ ¦ ¦ ¦-- field_registry.py ¦ ¦ ¦ ¦ +-- audit.py # NFR-04 audit trail ¦ ¦ ¦ +-- models/ ¦ ¦ +-- tests/ ¦ ¦ ¦-- test_scope_negative.py # BR-001 leakage tests ¦ ¦ ¦-- test_document_rbac.py # BR-007 / BR-008 ¦ ¦ +-- test_fnol_idempotency.py # NFR-37 ¦ ¦ ¦ +-- mock-externals/ ¦ +-- {ods_ccp,mdm,ecm,ccs}.py ¦ ¦-- db/ ¦ ¦-- schema.sql ¦ +-- seed/ ¦ ¦-- 01_hierarchy.sql 02_personas.sql 03_policies.sql ¦ +-- 04_claims.sql 05_documents.sql 06_field_registry.sql ¦ ¦-- config/ # <-- hot-reloadable. NFR-45 proof. ¦ ¦-- field-registry.json # Exhibit 5 attribute model ¦ ¦-- fnol-forms/ ¦ ¦ ¦-- _core.json # Steps 1 to 4b core intake ¦ ¦ ¦-- property-equipment.json # 6 fields ¦ ¦ ¦-- vehicle.json # 8 fields ¦ ¦ ¦-- cyber.json # 9 fields ¦ ¦ ¦-- marine.json # 10 fields ¦ ¦ ¦-- litigation.json # 13 fields ¦ ¦ +-- liability.json # 1 field ¦ ¦-- privileges.json # persona -> privilege matrix ¦ +-- countries/{US,ES,AE}.json ¦ +-- tests/ ¦-- e2e/ # Playwright: UJ-001, UJ-002 +-- a11y/ # axe-core, WCAG 2.2 AA

4.1  Structural decisions worth noting

Configuration is not code.  The config directory sits outside all source trees. Nothing in it requires a build step, which is what makes the NFR-45 demonstration possible.

The field registry is central.  Field visibility, ordering, PII masking and product-conditional groups are all resolved at runtime from the registry, never from hard-coded arrays. Exhibit 5 requires this explicitly.

Independent deployability.  The MFE has its own webpack config and can be built and deployed on its own cadence, satisfying DR-3.7.

Tests sit next to the enforcement point.  Negative security tests live beside the API, not in the end-to-end suite, so they run on every commit rather than nightly.

5.  Data Model

Seed the database so the demo is credible. Use the RFP's own worked example: a multi-site hospitality and airport concessions client whose claim profile is expressed as Airport to Location to Restaurant.

5.1  Core schema

-- MDM hierarchy surrogate (BS-04). Materialised path enables BR-001 in one query. org_nodes ( org_node VARCHAR(64) PK, -- 'CORP-HOSP','LOC-JFK','SITE-JFK-T4-BISTRO' parent_node VARCHAR(64) FK, path VARCHAR(512), -- '/CORP-HOSP/LOC-JFK/SITE-JFK-T4-BISTRO' level ENUM('corporate','location','site'), display_name VARCHAR(255), country_code CHAR(2) ) -- Exhibit 5 field attribute model. THIS TABLE IS THE DIFFERENTIATOR. field_registry ( field_key VARCHAR(64) PK, label_token VARCHAR(128), -- i18n key, never literal text available_in_meridian BOOLEAN, dynamic_category VARCHAR(64), -- 'Vehicle Details','Cyber','Marine' is_pii BOOLEAN, in_analytics_model BOOLEAN, show_on_claim_list BOOLEAN, show_on_claim_record BOOLEAN, show_on_client_analytics BOOLEAN, c2s_order INT, default_visibility ENUM('show','hide') ) claims ( aon_claim_id VARCHAR(32) PK, -- the ONLY external identifier org_node VARCHAR(64) FK, -- stamped at creation (BR-006) client_claim_ref VARCHAR(64), status, sub_status, claim_type, -- claim_type: 'Claim' ¦ 'Incident' global_product, global_product_category, carrier, carrier_policy_number, date_of_loss, date_reported_to_aon, date_reported_to_carrier, gross_incurred, total_paid, total_outstanding, applicable_deductible, sir_amount, loss_description, cause_of_loss, consequence_of_loss, loss_country, loss_city, loss_address, aon_claim_lead, aon_claim_lead_email, restricted_access BOOLEAN, -- gated by View Restricted Access Claims submitted_by, submitted_at, currency_code ) documents ( doc_id, claim_id FK, audience ENUM('client_visible','internal','carrier_only'), -- F-CC-09 provenance VARCHAR(64), -- 'client_provided_via_claims' -> BR-008 security_attr ENUM('default','internal','view_on_web', 'modify_on_web','access_controlled'), -- NFR-05 ecm_reference VARCHAR(512), -- ADR-001: reference only, never the blob doc_type, size_bytes, uploaded_at ) policies ( policy_id, org_node FK, -- policy-to-hierarchy mapping carrier_name, carrier_policy_number, cover_number, agreement_version, product_line, effective_date, expiration_date, active_for_fnol BOOLEAN, -- Policy Availability Management aon_contact_name, aon_contact_email ) fnol_outbox ( -- NFR-37 resilience submission_id UUID PK, idempotency_key VARCHAR(128) UNIQUE, payload JSON, state ENUM('queued','sent','acknowledged','failed'), attempts INT, last_error TEXT, created_at, sent_at ) users (okta_sub PK, org_node FK, persona_id, locale, groups JSON) audit_log (actor_sub, action, resource_type, resource_id, org_node, ts)

5.2  Seed volumes

| Entity | Volume | Rationale |
| --- | --- | --- |
| Client organisation | 1 | The hospitality and airport concessions example from the RFP |
| Organisational nodes | 1 corporate + 3 locations + 9 sites | Three levels, enough to prove downward-only inheritance |
| Persona users | 7 | One per persona defined in Exhibit 5 |
| Policies | 12 across 6 product lines | Enough to drive dynamic FNOL variation |
| Claims | 60 distributed across nodes | Large enough for pagination, filtering and credible KPI figures |
| Documents | 24, mixed audiences | Client-visible, internal and carrier-only on the same claims |
| Field registry rows | approximately 80 | Core claim fields from Exhibit 5 plus product-conditional fields |

SEEDING TIP Distribute the 60 claims deliberately so the persona switch is visually obvious: roughly 60 at corporate scope, 14 at the JFK location, 3 at the Terminal 4 restaurant site. A demo where the numbers barely change does not land the point.

6.  The Core Enforcement Function

Everything in Pillar 2 reduces to this one function. Get it right on Day 3 and every screen afterwards inherits correct behaviour. Get it wrong and no amount of UI polish will survive a security review.

# services/claims-api/app/auth/scope.py # Implements F-CC-07 / BR-001: assigned node plus all descendants. # Never peers. Never parents. async def resolve_authorized_scope(org_node: str, db) -> list[str]: """ BR-001: A Client User's organisational scope is the assigned node plus all descendant nodes (downward inheritance). Peer and parent nodes are excluded. """ row = await db.fetch_one( "SELECT path FROM org_nodes WHERE org_node = :n", {"n": org_node} ) if not row: raise HTTPException(403, "No valid organisational node") # BR-005 return [r["org_node"] for r in await db.fetch_all( "SELECT org_node FROM org_nodes WHERE path LIKE :p", {"p": f"{row['path']}%"} )] # Applied as a hard dependency on EVERY data route. No exceptions, no bypass. @router.get("/claims") async def list_claims(scope: list[str] = Depends(current_user_scope), ...): return await db.fetch_all( "SELECT * FROM claims WHERE org_node IN :scope ...", {"scope": scope} )

6.1  Two rules that make this defensible

Scope comes only from the validated JWT org_node claim.  Never from a query parameter, header or request body — those are client-controllable and therefore worthless as an authorisation input.

There is exactly one enforcement point.  If a reviewer can find a second place where scope is computed, a bypass has been created. Record this in ADR-POC-002 so the constraint survives team changes.

6.2  Negative tests — written on Day 3, before any UI exists

def test_location_manager_cannot_see_peer_location(): """BR-001: a LOC-JFK user must never see LOC-LHR claims.""" r = client.get("/claims", headers=auth_as("persona3_jfk")) assert all(c["org_node"].startswith("LOC-JFK") or c["org_node"].startswith("SITE-JFK") for c in r.json()["items"]) def test_site_manager_cannot_see_parent_location_claims(): """BR-001: upward inheritance is forbidden.""" r = client.get("/claims", headers=auth_as("persona5_bistro")) assert not any(c["org_node"] == "LOC-JFK" for c in r.json()["items"]) def test_org_node_query_param_cannot_override_jwt(): """Scope must come only from the token, never from the request.""" r = client.get("/claims?org_node=CORP-HOSP", headers=auth_as("persona5_bistro")) assert len(r.json()["items"]) == 3 # unchanged - parameter ignored

Workstream 3 of the RFP requires negative testing evidence that no user can access claims, documents or analytics outside their authorised organisational scope. Writing these tests first means that evidence is a by-product of the build rather than a retrofit.

7.  Sprint 0 — Foundation

Days 1 to 4. No screens are produced. This is the plumbing that everything else depends on.

7.1  Day 1 — Okta tenant and scaffold

Create a free tenant at developer.okta.com and configure as follows.

| Setting | Value |
| --- | --- |
| Application 1 | SPA, Authorization Code with PKCE, redirect http://localhost:3000/callback |
| Application 2 | Service application, Client Credentials (machine to machine) |
| Custom claim | org_node — string, sourced from user profile, added to the access token |
| Custom claim | groups — filter matching claims_*, added to the access token |
| Authorisation server | Custom server. The default server will not carry custom claims reliably. |

Persona users to create

| Persona | Example role | org_node | groups |
| --- | --- | --- | --- |
| 1 | C-Suite | CORP-HOSP | claims_viewer, claims_analytics, claims_export |
| 2 | Risk Manager (Client Admin) | CORP-HOSP | all of the above plus claims_client_admin |
| 3 | Location Manager (Airport Director) | LOC-JFK | claims_viewer, claims_fnol, claims_docs, claims_analytics |
| 4 | Functional Lead (HRBP) | LOC-JFK | claims_viewer, claims_fnol |
| 5 | Manager (Restaurant Manager) | SITE-JFK-T4-BISTRO | claims_viewer, claims_fnol, claims_docs |
| 6 | Employee / Reporter | SITE-JFK-T4-BISTRO | claims_fnol, claims_own_only |
| 7 | Unauthorised User | none | none |

Then scaffold the pnpm monorepo and bring MySQL up with docker-compose.

7.2  Day 2 — UUI stub

Build the component set below. The discipline that matters is exporting the same names and prop shapes expected from the Aon United UI package, so that the swap is a dependency change rather than a refactor.

Button IconButton TextField Textarea Select DatePicker Checkbox Radio Card PageHeader Tabs Breadcrumb Grid DataTable KpiTile StatusPill Timeline Badge Modal Toast Banner Spinner ErrorState EmptyState Stepper FileUpload FormField

Style with the Aon palette — navy #0F2B5B, red accent #E8112D, neutral greys, Inter or Calibri. Build aria attributes and focus management in from the first commit. NFR-49 states that accessibility compliance is built into each UUI component and that any non-UUI component requires a formal Design System team exception, so retrofitting WCAG 2.2 AA later is materially more expensive than building it in. Give every component a Storybook entry — that becomes the accessibility audit surface required by NFR-50.

7.3  Day 3 — Scope enforcement and field registry

FastAPI application with Okta JWKS validation middleware

resolve_authorized_scope() implemented exactly as section 6

field_registry table created, seeded, and exposed via GET /config/field-registry

The three negative tests from section 6.2 written and passing

7.4  Day 4 — Micro-Frontend injection

Module Federation configuration

// packages/shell/webpack.config.js new ModuleFederationPlugin({ name: "meridianShell", remotes: { claimsMfe: "claimsMfe@http://localhost:3001/remoteEntry.js" }, shared: { react: { singleton: true, requiredVersion: "^18.2.0" }, "react-dom": { singleton: true, requiredVersion: "^18.2.0" } } }) // packages/claims-mfe/webpack.config.js new ModuleFederationPlugin({ name: "claimsMfe", filename: "remoteEntry.js", exposes: { "./ClaimsApp": "./src/ClaimsApp" }, shared: { react: { singleton: true }, "react-dom": { singleton: true } } })

The shell-to-MFE contract

// packages/shell/src/mfe/MfeHost.tsx const ClaimsApp = React.lazy(() => import("claimsMfe/ClaimsApp")); <MfeErrorBoundary fallback={<ClaimsUnavailable />}> {/* DR-3.4 */} <Suspense fallback={<Spinner />}> <ClaimsApp authToken={accessToken} /* DR-3.1 */ orgNode={claims.org_node} userGroups={claims.groups} locale={user.locale} claimId={deepLinkClaimId ?? null} /* DR-3.5 prop hand-off at mount */ onEvent={shellEventBus.emit} /* DR-3.8 */ /> </Suspense> </MfeErrorBoundary>

SPRINT 0 GATE Do not proceed to Screen 1 until all four of these pass: (1) the shell loads the MFE over the network at runtime; (2) logging in as Persona 3 returns only JFK-scoped claims; (3) throwing inside the MFE leaves shell navigation working; (4) all three negative scope tests are green.

8.  Screen 1 — Claims Landing Page

Days 5 to 7.  Traceability: Figure 1, Epic 1 (6 features), Functional Requirements – Core Claims Experience.

8.1  Layout

+----------------------------------------------------------------+ ¦ = Aon Meridian Claims v Policies Documents (3) AK v ¦ <- SHELL +----------------------------------------------------------------+ ¦ ¦ ¦ Good morning, Sarah [Corporate HQ v] ¦ <- entity switcher ¦ Hospitality Group - 3 locations ¦ ¦ ¦ ¦ +----------+----------+----------+----------+----------+ ¦ ¦ ¦ Total ¦ Average ¦ Total ¦ Total ¦ Largest ¦ ¦ ¦ ¦ Gross ¦ Gross ¦ Out- ¦ Paid ¦ Claim ¦ ¦ ¦ ¦ Incurred ¦ Incurred ¦ standing ¦ ¦ ¦ ¦ ¦ ¦ $4.2M ¦ $70.1K ¦ $1.8M ¦ $2.4M ¦ $412K ¦ ¦ ¦ ¦ ^ 12% YoY¦ v 3% YoY ¦ ^ 8% YoY ¦ ^ 15% YoY¦ CLM-0042 ¦ ¦ ¦ +----------+----------+----------+----------+----------+ ¦ ¦ ¦ ¦ +--- Quick Actions ------------------------------------+ ¦ ¦ ¦ [+ Report a Claim] [View My Claims] [Contact Aon] ¦ ¦ ¦ +-----------------------------------------------------+ ¦ ¦ ¦ ¦ +--- Recent Claims ----------------+--- Resources ----+ ¦ ¦ ¦ CLM-0061 Property Open $82K ¦ - Claims Guide ¦ ¦ ¦ ¦ CLM-0060 Motor Review $14K ¦ - FNOL Checklist ¦ ¦ ¦ ¦ CLM-0058 Liability Closed $31K ¦ - Aon Service ¦ ¦ ¦ ¦ View all 60 claims ->¦ ¦ ¦ ¦ +----------------------------------+------------------+ ¦ +----------------------------------------------------------------+

8.2  Functionality checklist

| # | Behaviour | Trace |
| --- | --- | --- |
| 1 | Five KPI tiles: Total Gross Incurred, Average Gross Incurred, Total Outstanding, Total Paid, Largest Claim | Figure 1 |
| 2 | Each tile shows year-on-year movement with a direction indicator | Figure 1 |
| 3 | All figures scoped to the caller's org_node — same endpoint, different persona, different numbers | BR-002 |
| 4 | Entity switcher appears only when the user's node has descendants; re-scopes the whole page | Epic 1 |
| 5 | Quick actions: Report a Claim, View My Claims, Contact Aon | Epic 1 |
| 6 | Report a Claim disabled with an explanatory tooltip when the claims_fnol group is absent | BR-005 |
| 7 | Recent claims list showing the five most recent in scope; row click opens Claim Detail | Epic 1 |
| 8 | Notification bell with unread count, opening the notification centre | Epic 1, Epic 8 |
| 9 | Currency renders per user locale; layout flips for right-to-left locales | NFR-42, NFR-44 |
| 10 | Persona 7 sees an access-denied state, not an empty dashboard | Persona 7 |

8.3  API contract

GET /api/v1/summary Authorization: Bearer <jwt> 200 { "org_node": "LOC-JFK", "scope_node_count": 4, "kpis": { "total_gross_incurred": { "value": 1240000, "currency": "USD", "yoy_pct": 12.4 }, "avg_gross_incurred": { "value": 70100, "currency": "USD", "yoy_pct": -3.1 }, "total_outstanding": { "value": 540000, "currency": "USD", "yoy_pct": 8.0 }, "total_paid": { "value": 700000, "currency": "USD", "yoy_pct": 15.2 }, "largest_claim": { "value": 412000, "currency": "USD", "aon_claim_id": "CLM-0042" } }, "recent_claims": [ /* five items */ ], "entitlements": { "can_report_claim": true, "can_export": false, "can_view_analytics": true } }

ACCEPTANCE Log in as Personas 1, 3 and 5 in sequence. Three different KPI sets, three different entity switcher states, every response inside three seconds per NFR-26.

9.  Screen 2 — Claims List

Days 8 to 10.  Traceability: Figure 3, Epic 3, Exhibit 5 field model.

9.1  Layout

+----------------------------------------------------------------+ ¦ Claims [+ Report a Claim] ¦ ¦ ¦ ¦ +- Submitted (58) -+- Drafts (2) -+ <- Figure 3 tabs ¦ ¦ ¦ ¦ ¦ ¦ [Search claims, policies, descriptions... ] ¦ ¦ ¦ ¦ ¦ ¦ Status v Sub-Status v Product v Sub-Product v ¦ ¦ ¦ Date of Loss v [Columns] [Export] ¦ ¦ ¦ ¦ ¦ ¦ Aon Claim ID¦Policy No ¦Product ¦Lead Insurer¦DoL ¦Status¦ ¦ ¦ ------------+----------+---------+------------+------+------¦ ¦ ¦ CLM-0061 > ¦POL-88213 ¦Property ¦Zurich ¦12 Aug¦ Open ¦ ¦ ¦ CLM-0060 > ¦POL-88109 ¦Motor ¦AXA ¦08 Aug¦ Rev'w¦ ¦ ¦ CLM-0058 > ¦POL-88213 ¦Liability¦Zurich ¦01 Aug¦ Clsd ¦ ¦ ¦ ¦ ¦ ¦ <- 1 2 3 ... 6 -> Showing 1-10 of 58 ¦ ¦ +--------------------------------------------------------------+ +----------------------------------------------------------------+

9.2  Functionality checklist

| # | Behaviour | Trace |
| --- | --- | --- |
| 1 | Submitted and Drafts tabs; drafts are the user's own incomplete FNOL submissions | Figure 3 |
| 2 | Columns per Figure 3: Aon Claim ID, Policy Number, Product Line, Lead Insurer, Date of Loss, Status, Loss Description, Submitter, Submission Date | Figure 3 |
| 3 | Four-dimension filtering: status, sub-status, product, sub-product | Figure 3 |
| 4 | Configurable columns driven by field_registry, not a hard-coded array | Exhibit 5 |
| 5 | Column order from c2s_order; default visibility from default_visibility | Exhibit 5 |
| 6 | PII-flagged fields masked unless the claims_view_pii privilege is held | Exhibit 5, NFR-04 |
| 7 | Rows with restricted_access hidden unless claims_view_restricted is held | Exhibit 5 |
| 8 | Server-side pagination, sorting and filtering with payload limits | NFR-34 |
| 9 | Advanced multi-criteria search plus saved and shareable views | Epic 3 |
| 10 | Export to Excel and PDF, gated on claims_export, honouring PII masking | Epic 3, WS1 |
| 11 | Only aon_claim_id displayed anywhere — no Meridian or legacy identifiers | Single Claim Identifier Experience |
| 12 | Persona 6 sees only claims where submitted_by equals self | Persona 6 |

9.3  The config-driven column pattern

This is what proves configurable rather than bespoke. Build it this way from the first commit.

// WRONG - this is the bespoke pattern the RFP explicitly rejects const columns = [ { key: 'aon_claim_id', label: 'Claim ID' }, { key: 'status', label: 'Status' }, ]; // RIGHT - Exhibit 5's attribute model, resolved at runtime const { fields } = useFieldRegistry(); const { canViewPii } = useEntitlements(); const columns = fields .filter(f => f.available_in_meridian && f.show_on_claim_list) .sort((a, b) => a.c2s_order - b.c2s_order) .map(f => ({ key: f.field_key, label: t(f.label_token), hidden: f.default_visibility === 'hide', render: f.is_pii && !canViewPii ? maskValue : undefined, }));

ACCEPTANCE Set show_on_claim_list to false for one field in config/field-registry.json and refresh the browser. The column disappears with no rebuild and no redeploy. That is live NFR-45 evidence, and it is the moment the configurability argument stops being a claim.

10.  Screen 3 — Claim Detail

Days 11 to 13.  Traceability: Figure 4, Epic 3 (Claim 360), Pillar 1.

10.1  Layout

+----------------------------------------------------------------+ ¦ <- Claims ¦ ¦ ¦ ¦ CLM-0061 * Open ¦ ¦ Water damage - Terminal 4 Bistro kitchen ¦ ¦ Your reference: HG-2026-0417 Reported 12 Aug 2026 ¦ ¦ ¦ ¦ +--- Financials -----------------------------------------+ ¦ ¦ ¦ Total Incurred ¦ Deductible ¦ Carrier Insurance ¦ SIR ¦ ¦ ¦ ¦ $82,400 ¦ $10,000 ¦ $72,400 ¦ $25K ¦ ¦ ¦ +--------------------------------------------------------+ ¦ ¦ ¦ ¦ *-------*-------*-------o-------o ¦ ¦ Reported Review Reserve Payment Closed ¦ ¦ 12 Aug 14 Aug 18 Aug - - ¦ ¦ ¦ ¦ +- Details -+- Documents(4) -+- Contacts -+- Activity -+ ¦ ¦ ¦ ¦ ¦ ¦ ¦ Description of Loss ¦ ¦ ¦ ¦ Burst pipe above kitchen ceiling caused water ¦ ¦ ¦ ¦ ingress overnight. Equipment and stock affected. ¦ ¦ ¦ ¦ ¦ ¦ ¦ ¦ Cause of Loss Water Damage - Escape of Water ¦ ¦ ¦ ¦ Product Property & Equipment ¦ ¦ ¦ ¦ Carrier Zurich (POL-88213) ¦ ¦ ¦ ¦ Aon Claim Lead M. Reeves - m.reeves@aon.com ¦ ¦ ¦ ¦ ¦ ¦ ¦ ¦ +- Loss Location -----------------+ ¦ ¦ ¦ ¦ ¦ [ map - JFK Terminal 4 ] ¦ ¦ ¦ ¦ ¦ +---------------------------------+ ¦ ¦ ¦ +-------------------------------------------------------+ ¦ +----------------------------------------------------------------+

10.2  Functionality checklist

| # | Behaviour | Trace |
| --- | --- | --- |
| 1 | Header: Aon Claim ID, status pill, client reference, loss name | Figure 4 |
| 2 | Financials band: Total Incurred, Deductible, Carrier Insurance, SIR | Figure 4 |
| 3 | Status timeline: Reported, Under Review, Reserve Set, Payment, Closed with dates | Epic 3 |
| 4 | Narrative loss description alongside structured loss fields | Figure 4 |
| 5 | Location map for the loss address | Figure 4 |
| 6 | Documents tab returns only audience = client_visible, filtered server-side | BR-007, F-CC-09 |
| 7 | Document search within the claim | Figure 4 |
| 8 | Upload gated on claims_upload_docs; files up to 100 MB | NFR-29 |
| 9 | Contacts tab with Aon claim lead and client contacts; messaging gated on privilege | Core Claims Experience |
| 10 | Activity and notes tab | Epic 3 |
| 11 | Direct URL access to an out-of-scope claim returns 403, not 404, and is audit-logged | BR-001 |
| 12 | Product-conditional field groups render from dynamic_category | Exhibit 5 |

10.3  Document access — the Pillar 1 pattern

# services/claims-api/app/services/sdms_proxy.py # ADR-001: files stay in ECM; S-DMS holds references and gates access. async def list_claim_documents(claim_id: str, scope: list[str], privileges: set, db): # 1. Claim must be inside the caller's organisational scope (BR-001) claim = await get_claim_in_scope(claim_id, scope, db) if not claim: await audit.log_denied("document_list", claim_id) raise HTTPException(403) # 2. Client users see ONLY client_visible. # Never internal. Never carrier_only. docs = await db.fetch_all(""" SELECT doc_id, doc_type, size_bytes, uploaded_at, security_attr FROM documents WHERE claim_id = :cid AND audience = 'client_visible' AND NOT (provenance = 'client_provided_via_claims' AND :is_broker) -- BR-008 """, {"cid": claim_id, "is_broker": "aon_broker" in privileges}) # 3. NFR-05 document-level attribute check visible = [d for d in docs if d["security_attr"] != "internal"] # 4. The ECM reference is NEVER returned to the client - proxy URL only return [{**d, "url": f"/api/v1/documents/{d['doc_id']}/content"} for d in visible]

ACCEPTANCE Seed CLM-0061 with four client-visible, two internal and one carrier-only document. The client user sees exactly four. Requesting the internal document by ID returns 403 with an audit row. That single test is the BR-007 and BR-008 evidence Workstream 3 asks for.

11.  Screen 4 — FNOL Wizard

Days 14 to 20.  Traceability: Figure 5, Epic 2, Exhibit 4 field inventory, Dynamic FNOL requirements.

PRIORITY The RFP calls FNOL the highest-value and highest-risk element of the client experience. Budget the most time here. It is also where the configurable-not-bespoke argument is won or lost.

11.1  Step mapping

Figure 5 describes five steps while Exhibit 4 lists steps 4a and 4b separately. Reconcile them as follows and state the reconciliation in the design documentation.

| Wizard step | Exhibit 4 source | Content |
| --- | --- | --- |
| 1 — Incident Details | Step 1 | Date of Loss, Site / Location, Claim or Incident type |
| 2 — Policy Selection | Step 2 | Nine read-only policy fields sourced from ODS or CCP |
| 3 — Loss Details | Step 3 | Core loss fields plus product-specific conditional groups |
| 4 — Documents & Contacts | Steps 4a and 4b | Upload with camera capture, plus contact management |
| 5 — Accept & Submit | Figure 5 | Review summary, attestation, submission |

11.2  Step 1 — Incident Details

Step 1 of 5 *---o---o---o---o [Save & Exit] Date of Loss * [ 12 Aug 2026 [cal] ] Site / Location * [ JFK T4 - Bistro v ] -> scoped to your org_node Type * ( ) Incident (*) Claim -> default from country config [ Continue -> ]

The site dropdown lists only sites within the caller's authorised scope (BR-001).

Site and Date of Loss together drive which policies appear in Step 2 — stated explicitly in Figure 5.

The Claim versus Incident default comes from country configuration, and is configurably locked or unlocked.

Save and Exit persists a draft from Step 1 onward, and the draft appears on the Claims List Drafts tab.

11.3  Step 2 — Policy Selection (all read-only from ODS / CCP)

Step 2 of 5 *---*---o---o---o Policies available for JFK T4 - Bistro on 12 Aug 2026 +------------------------------------------------------+ ¦ (*) POL-88213 - Property & Equipment ¦ ¦ Zurich - Cover 004 - v2 - 01 Jan to 31 Dec 2026 ¦ ¦ Aon contact: M. Reeves ¦ +------------------------------------------------------+ ¦ ( ) POL-88109 - Motor Fleet ¦ ¦ AXA - Cover 001 - v1 - 01 Jan to 31 Dec 2026 ¦ +------------------------------------------------------+

Nine read-only fields per Exhibit 4: Policy Period, Lead Carrier Name, Carrier Policy Number, Cover Number, Agreement Version, Client Name, Product Line, Aon Contact Name and Aon Contact Email. Only policies with active_for_fnol set to true appear, satisfying Policy Availability Management. The selected Product Line is the trigger for Step 3's dynamic field groups.

11.4  Step 3 — Loss Details and dynamic product fields

This is the heart of the POC.

Step 3 of 5 *---*---*---o---o -- Core Loss Details ----------------------------- Named Insured [ Hospitality Group Inc. ] Loss Country * [ United States v ] Loss Location [ JFK T4, Queens NY ] Who experienced loss? * ( ) 1st party ( ) 3rd party ( ) Both Loss Description * [ ] [ 0/2000] Cause of Loss * [ Escape of Water v ] <- filtered by product Claim Currency * [ USD v ] Initial Reserve [ ] Client Claim Reference [ HG-2026-0417 ] -- Property & Equipment -------------- <- APPEARS FROM CONFIG First or Third Party * [ First Party v ] Item Name [ Walk-in refrigeration ] Serial / Inventory No. [ ] Damage Description [ ] Owner Contact [ ] -- Loss Circumstances ---------------- <- ALSO FROM CONFIG Loss Severity [ Moderate v ] Weather Conditions [ v ] Area of Accident [ Kitchen ] CCTV Captured? ( ) Yes (*) No Consequence of Loss [ Business Interruption v ]

The engine — driven by JSON, not code

// config/fnol-forms/property-equipment.json { "dynamic_category": "Property & Equipment", "applies_when": { "product_line": ["Property", "Property & Equipment"] }, "label_token": "fnol.group.property_equipment", "fields": [ { "key": "first_or_third_party", "type": "select", "required": true, "options_source": "static", "options": ["First Party", "Third Party"] }, { "key": "item_name", "type": "text" }, { "key": "serial_inventory_no", "type": "text" }, { "key": "owner_contact", "type": "text", "pii": true }, { "key": "damage_description", "type": "textarea", "max_length": 1000 }, { "key": "owner_contact_notes", "type": "textarea" } ] }

// packages/claims-mfe/src/screens/fnol/engine/DynamicFormEngine.tsx export function DynamicFormEngine({ productLine, country, claimType, values, onChange }) { const { groups } = useFnolConfig(); // fetched, cached, hot-reloadable const active = groups.filter(g => matches(g.applies_when, { productLine, country, claimType, ...values }) ); return active.map(group => ( <FieldGroup key={group.dynamic_category} title={t(group.label_token)}> {group.fields.map(f => ( <DynamicField key={f.key} spec={f} value={values[f.key]} onChange={onChange} /> ))} </FieldGroup> )); }

Build all eleven product groups

They are only JSON files, so the marginal cost per group is minutes. Having all eleven present is far more persuasive than demonstrating two, because it shows the engine rather than a special case.

| Group | Fields | Group | Fields |
| --- | --- | --- | --- |
| Vehicle Details | 8 | Property & Equipment | 6 |
| Cyber | 9 | EL / WC | 1 |
| Litigation | 13 | Liability | 1 |
| Marine | 10 | Construction | 1 |
| Entertainment | 6 | Client Specific | 27 |
| Loss Circumstances | 5 |  |  |

11.5  Step 4 — Documents and Contacts

Step 4 of 5 *---*---*---*---o -- Documents ------------------------------------- +------------------------------------------------+ ¦ Drag files here or [Browse] - [Camera] ¦ ¦ Up to 100 MB per file ¦ +------------------------------------------------+ v plumber-invoice.pdf 2.4 MB Invoice v x v kitchen-damage-01.jpg 4.1 MB Photo v x ! Required for Property claims: Photographs (v) - Repair Estimate (x) -- Contacts -------------------------------------- [+ Add Contact] +------------------------------------------------+ ¦ Maria Santos - Site Manager ¦ ¦ m.santos@hospgroup.com - +1 718 555 0142 ¦ ¦ [x] Can view [ ] Can modify [x] Include on emails ¦ +------------------------------------------------+

Camera capture via an input element with capture set to environment, per Epic 2.

Required-document rules by product and country come from configuration and can optionally block submission.

Contact fields per Exhibit 4 Step 4b, including the three permission checkboxes: can view claims, can modify claims, include on emails.

11.6  Step 5 — Accept and Submit

A full read-only summary with per-section edit links, an attestation checkbox, then submission. The confirmation screen shows the Aon Claim ID only, suppressing Meridian and legacy acknowledgement identifiers as the Single Claim Identifier Experience requirement demands.

11.7  Resilient submission — the strongest differentiator

The RFP requires that a client can still submit successfully when Claims Copilot is unavailable, with no client-visible impact. Implement it as a durable outbox with an idempotency key.

# services/claims-api/app/services/outbox.py @router.post("/fnol", status_code=202) async def submit_fnol(payload: FnolSubmission, idem_key: str = Header(alias="Idempotency-Key"), scope=Depends(current_user_scope), user=Depends(current_user)): # Replay protection - safe retries from a flaky mobile connection if existing := await db.find_by_idem_key(idem_key): return existing.receipt if payload.site_org_node not in scope: # BR-005 raise HTTPException(403) # Durable write FIRST. Always succeeds. # This is why the client never experiences the outage. submission = await db.insert_outbox( idempotency_key=idem_key, payload=payload.dict(), org_node=payload.site_org_node, # BR-006 stamp state="queued" ) try: claim_id = await claims_copilot.create_claim(payload, timeout=3.0) await db.mark_sent(submission.id, claim_id) return {"aon_claim_id": claim_id, "state": "acknowledged"} except (Timeout, ServiceUnavailable): # Client still receives a receipt. A worker reconciles later. return {"receipt_id": submission.id, "state": "queued", "message": "Your claim has been received. " "Your claim number will be emailed shortly."}

THE DEMO MOMENT Demonstrate this live. On Step 5, stop the Claims Copilot container and click Submit. The user receives a success receipt. Restart the container and the reconciliation worker issues the real claim number and fires the notification. In a clarification session that moment lands harder than any slide, because it answers a Must requirement that most responses will only assert.

12.  Screen 5 — Notifications and Deep Link

Days 21 to 22.  Traceability: Epic 8, Core Claims Experience, DR-3.5, F-MER-04.

12.1  The requirement that catches people out

The RFP states that every user notification, in whichever channel it is delivered, shall carry a direct link to the relevant claim, task or document, and that the link must survive authentication — so a user who is not already signed in is authenticated via the Okta PKCE flow and then landed on the intended record rather than a generic home page.

+-- Notifications ------------------------- [Preferences] ---+ ¦ * Reserve set on CLM-0061 2 hours ago ¦ ¦ Reserve of $82,400 has been set [View Claim ->] ¦ ¦ * Document requested - CLM-0058 1 day ago ¦ ¦ Your adjuster has requested a repair estimate ¦ ¦ o Claim CLM-0055 closed 3 days ago ¦ +------------------------------------------------------------+

12.2  The PKCE state round-trip

// packages/shell/src/auth/deepLinkState.ts // 1. An unauthenticated user opens /claims/CLM-0061 from an email link export function beginAuthWithDeepLink(intendedPath: string) { const state = btoa(JSON.stringify({ nonce: crypto.randomUUID(), deepLink: intendedPath, // <- survives the Okta round trip })); oktaAuth.signInWithRedirect({ state }); // F-MER-04 } // 2. Okta returns to /callback?code=...&state=... export function resolveDeepLink(returnedState: string): string ¦ null { const { deepLink } = JSON.parse(atob(returnedState)); return deepLink ?? null; } // 3. The shell extracts the claim ID and passes it as a prop at mount (DR-3.5) const claimId = parseClaimId(resolveDeepLink(state)); <ClaimsApp claimId={claimId} ... /> // MFE opens Claim Detail directly

ACCEPTANCE In a fresh incognito window, paste /claims/CLM-0061. You should get the Okta login and then land on Claim Detail for CLM-0061, not the dashboard. Also verify that if the target claim is outside your scope you land on a clean 403 page rather than leaking the claim's existence.

13.  Screen 6 — Analytics Placeholder

Day 23.  Traceability: Figure 2, Epic 4 — explicitly ACIA-delivered and out of scope for the Provider.

Handle this precisely, because it is a scope-discipline signal. The RFP states three times that the Claims Analytics build is delivered by the ACIA team and is out of scope, while the presentation of analytics within the client experience remains in Workstream 1.

+-- Claims Analytics ----------------------------------------+ ¦ ¦ ¦ +-----------------------------------------------------+ ¦ ¦ ¦ Analytics delivered by Aon ACIA ¦ ¦ ¦ ¦ ¦ ¦ ¦ ¦ This surface renders the ACIA analytics component. ¦ ¦ ¦ ¦ Provider scope: presentation, scope-filtered data ¦ ¦ ¦ ¦ context (BR-002), and drill-down routing into the ¦ ¦ ¦ ¦ claims list and claim record. ¦ ¦ ¦ ¦ ¦ ¦ ¦ ¦ [ mock dashboard - Overview ¦ Loss Location ¦ Fin ] ¦ ¦ ¦ +-----------------------------------------------------+ ¦ ¦ ¦ ¦ v org_node scope context passed to analytics (BR-002) ¦ ¦ v Drill-down to Claims List with filter applied ¦ +-------------------------------------------------------------+

Build the integration contract rather than the analytics: the container, the scoped data context you would hand to ACIA, the filter and benchmark toggle shell, and working drill-down navigation. This demonstrates that you know exactly where your delivery boundary sits, which is itself worth evaluation marks.

14.  Screen 7 — Admin Configuration Console

Days 24 to 25.  Traceability: NFR-45, Exhibit 5, configurable rather than bespoke.

This is not a client-facing screen. Build it anyway. It is the most persuasive artefact in the entire POC, because it turns the central claim of the response into something Aon can watch happen in real time.

+-- Configuration Console -----------------------------------+ ¦ +- Field Registry -+- FNOL Forms -+- Privileges -+- Countries -+ ¦ ¦ ¦ ¦ ¦ ¦ Field List Record PII Order ¦ ¦ ¦ ¦ -------------------------------------------------- ¦ ¦ ¦ ¦ Aon Claim ID [x] [x] [ ] 1 ¦ ¦ ¦ ¦ Status [x] [x] [ ] 2 ¦ ¦ ¦ ¦ Named Insured [x] [x] [x] 5 ¦ ¦ ¦ ¦ Aon Claim Lead [ ] [x] [ ] 12 ¦ ¦ ¦ ¦ ¦ ¦ ¦ ¦ [ Apply - no deployment required ] ¦ ¦ ¦ +--------------------------------------------------------+ ¦ +-------------------------------------------------------------+

14.1  The demo moment

Tick Aon Claim Lead under the List column, click Apply, switch to the Claims List tab and refresh. The column is there. No build, no deployment. Then say: that is how a new country, client or product line gets onboarded — configuration, not engineering.

That single interaction addresses the requirement stated in the RFP introduction — that the solution must be configurable rather than bespoke so that additional countries and clients can be onboarded without further engineering — and it addresses NFR-45, which requires that authorised configuration changes take effect without code modification or deployment.

14.2  Console tabs to build

| Tab | Controls | Proves |
| --- | --- | --- |
| Field Registry | Per-field toggles for list, record, analytics surfaces; PII flag; column order | Exhibit 5 attribute model, NFR-45 |
| FNOL Forms | Product group enable / disable, field required toggles | Dynamic FNOL Forms configurable requirement |
| Privileges | Persona to privilege matrix across the five privilege groups | RBAC model, NFR-04 |
| Countries | Locale, currency, claim-versus-incident default, required documents | NFR-42, NFR-44, Country-Specific rules |

15.  Tier 1 Thin Slice — Seven Days

If something demoable is needed by 28 August, cut to exactly this. Everything else waits.

| Day | Deliverable |
| --- | --- |
| 1 | Okta tenant with three personas (C-Suite, Airport Director, Restaurant Manager), monorepo scaffold, MySQL running |
| 2 | UUI stub — twelve components only: Button, Card, DataTable, KpiTile, StatusPill, TextField, Select, DatePicker, Stepper, Modal, Banner, FileUpload |
| 3 | Scope enforcement, three negative tests green, field registry table seeded |
| 4 | Module Federation working, shell to MFE prop contract, error boundary containment |
| 5 | Landing page with five scoped KPI tiles, plus Claims List with config-driven columns |
| 6 | Claim Detail with document audience filtering, plus FNOL Steps 1 to 3 with two dynamic groups |
| 7 | FNOL Steps 4 and 5, resilient submit demonstration, right-to-left locale toggle, demo rehearsal |

15.1  Deliberately deferred to Tier 2

Notification centre, admin configuration console, analytics placeholder, saved views, export to Excel and PDF, the location map, the remaining nine product field groups, and native mobile applications. Say this explicitly in the demo — declaring what was deliberately left out reads as control, whereas being caught missing something reads as oversight.

16.  Demo Script — Twelve Minutes

| # | Beat | What to say |
| --- | --- | --- |
| 1 | Log in as C-Suite | One Meridian portal. Claims is a Micro-Frontend loaded at runtime — separate deployment, separate team. |
| 2 | Show KPIs: 60 claims, $4.2M | Corporate scope. Everything. |
| 3 | Switch to Airport Director | Same URL, same code. 14 claims, $1.2M. Scope comes from the Okta org_node claim and is enforced server-side — the browser never decides. |
| 4 | Switch to Restaurant Manager | Three claims. The peer restaurant's claims are not filtered in the UI — the API never returned them. |
| 5 | Open a claim, then Documents | Four documents. There are seven on this claim; three are internal or carrier-only. BR-007 and BR-008 enforced in the S-DMS proxy. |
| 6 | Paste an out-of-scope claim URL | 403 and an audit entry. Not a 404 — we do not leak existence either. |
| 7 | Start FNOL, select the Property policy | Product Line comes from ODS. Watch Step 3. |
| 8 | Step 3 — groups appear | Property & Equipment and Loss Circumstances rendered from JSON configuration. Eleven groups configured, zero product-specific code. |
| 9 | Stop the Claims Copilot container | Now Claims Copilot is down. |
| 10 | Submit anyway, receive a receipt | The client is unaffected. Durable outbox, idempotency key. NFR-37. |
| 11 | Restart — claim number arrives | Reconciled. Claim number issued, notification sent. |
| 12 | Admin console — add a column | New field on the claims list. No deployment. That is how country eleven gets onboarded. |
| 13 | Switch locale to Arabic | Right-to-left layout, resource files, no code change. NFR-42 and NFR-44. |

REHEARSAL NOTE Rehearse beats 9 to 11 more than any other part. Stopping a container live is the highest-risk and highest-reward moment in the demo. Have a recorded fallback ready in case the environment misbehaves in the room.

17.  Compliance Evidence

Two documents turn a demo into a submission asset. Both should live in the POC repository and be referenced directly from the proposal.

17.1  Meridian Pattern alignment

| Layer | Mandatory adoption rule | POC status |
| --- | --- | --- |
| 1 — UUI | UI built from the United UI control set | Stub with an identical export surface; the swap is one dependency change. Accessibility built into each component. |
| 2 — Identity | Authentication delegated to Okta; custom identity stores not permitted | Satisfied for real. Okta PKCE with JWKS validation. Zero credential storage anywhere in the stack. |
| 2b — RBAC | Roles defined and enforced centrally in Meridian | org_node and groups claims consumed from the token; single enforcement point recorded in ADR-POC-002. |
| 3 — Agents | Vertex AI is the approved agentic orchestration layer | Not used. No AI features are in POC scope, so no exception is required. |
| 6 — Data | Databricks for analytical assets; no siloed application databases for cross-cutting data | MySQL is transactional only. The transactional-to-analytical boundary is documented; ACIA owns the analytics build. |
| 7 — Development | Claude Code is the standard AI coding assistant | Satisfied for real. Used throughout; the .claude configuration is committed to the repository. |

17.2  NFR compliance matrix

The RFP requires a per-requirement response to each of the 51 non-functional requirements, stating Comply, Comply with Qualification or Not Comply, with a supporting note and the proposed method of verification. Drafting that matrix against a working build rather than a design makes each answer concrete. The POC directly evidences the following subset.

| NFR | Requirement | POC evidence |
| --- | --- | --- |
| NFR-01, 33 | Okta single sign-on; authentication delegated in all cases | Real Okta PKCE flow in the shell |
| NFR-04 | Role-based authorisation across functionality, data and documents | Privilege guards plus server-side scope enforcement |
| NFR-05 | Two levels of document security, node and document level | audience plus security_attr columns, enforced in the proxy |
| NFR-26 | 99 per cent of standard interactions within three seconds | Measured on the landing page and claims list |
| NFR-29 | Files up to 100 MB without corruption | Upload path tested at the limit |
| NFR-34 | Throttling, rate limiting, pagination, payload limits | Server-side pagination and payload caps on list endpoints |
| NFR-37 | Critical workflows available under partial component failure | Durable outbox demonstrated live with the backend stopped |
| NFR-42, 44 | Multilingual including right-to-left; locale without code change | Five locales including Arabic, switched at runtime |
| NFR-43 | All user-facing text externalised into resource files | No literal strings in components; label tokens throughout |
| NFR-45 | Configuration changes without code modification or deployment | Admin console applying field registry changes live |
| NFR-48, 49 | WCAG 2.2 Level AA via UUI components | axe-core suite plus keyboard-only navigation pass |

18.  Open Questions for Aon

The question deadline is 21 August 2026. Two items in the RFP would materially change POC scope and delivery effort if clarified, and both are worth raising before the deadline closes.

18.1  United UI access timing

NFR-49 makes the United UI control set mandatory and requires a formal Design System team exception for any component not sourced from it. NFR-38 additionally requires compliance with the Aon Corporate Standard UI style guide, verified through design review.

Ask when the selected Provider receives United UI repository and Figma Code Connect access. If that access is only granted post-contract, the M3 Design and MVP Completion milestone on 6 November 2026 carries UI rework risk that should either be priced or explicitly flagged as an assumption in the response.

18.2  The client hierarchy contradiction

The RFP contains two statements that imply different architectures and materially different RBAC build effort.

| Location | Statement |
| --- | --- |
| Client Organisation Hierarchy and Scope Rule | The hierarchy model should accommodate varying client organisational structures without assuming a fixed number of levels or dependency on an external master data management (MDM) hierarchy. |
| Architecture Decisions (already taken) | The solution shall leverage MDM as the foundational source for client organisational hierarchies used in scope and access-control decisions, while providing the capability to manage, override and maintain hierarchy structures within the application where required. |

Ask which is authoritative. The answer determines whether the scope resolver reads from MDM at query time or from application-managed entity groupings in CCP, and it interacts with open item R-14 covering the MDM to Okta organisational scope binding mechanism and its refresh frequency — which the RFP itself notes determines entitlement latency and the joiner, mover and leaver revocation window.

18.3  Secondary items worth confirming

The final country and client list for the initial 2026 rollout, which determines localisation and configuration volume.

ODS readiness per country. ODS build is out of scope but the client experience depends on ODS-sourced policy data being available and of sufficient quality.

Whether the native iOS and Android applications are expected at the 15 February 2027 launch or may follow the responsive web experience, given the RFP text carries both a single-responsive-web statement and a native-application requirement in the same sentence.

Appendix A — Traceability Summary

| POC artefact | RFP source |
| --- | --- |
| Landing page, five KPI tiles | Figure 1; Epic 1 |
| Claims list, Submitted and Drafts tabs | Figure 3; Epic 3 |
| Claim detail, financials band with SIR | Figure 4; Epic 3 |
| Five-step FNOL wizard | Figure 5; Epic 2; Exhibit 4 |
| Eleven product-conditional field groups | Exhibit 4, Product-Specific Field Groups |
| Field registry attribute model | Exhibit 5, Claims List and Claim Record Field Model |
| Seven personas and privilege groups | Exhibit 5, RBAC Access Levels and Personas |
| Organisational scope enforcement | BR-001, BR-002, BR-005, BR-006; F-CC-07 |
| Document provenance and audience filtering | BR-003, BR-007, BR-008; ADR-001; F-CC-09 |
| Micro-Frontend injection and error containment | ADR-003; DR-3.1 to DR-3.8 |
| Deep link surviving authentication | F-MER-04; DR-3.5; Core Claims Experience |
| Resilient FNOL submission | NFR-37; Standard Functionality, API Functionality (resilience) |
| Configuration without deployment | NFR-45; Configurable Functionality, Rules Engine |
| Localisation including right-to-left | NFR-42, NFR-43, NFR-44; Epic 6 |
| Accessibility conformance | NFR-48, NFR-49, NFR-50 |
| Meridian Pattern layer adoption | Architecture Requirements, Mandatory Adoption Rules |

— End of document —